ERP Implementation Schedule & Build Plan

90-day delivery blueprint + 60-day hypercare, aligned to the process described in the meeting transcript

Planning basis: The meeting mentions a 10-day demo target, a 90-day working/support period, 30 days of training/monitoring and a further 60 days of support. The schedule below converts those commitments into a practical build sequence. It is a proposed delivery schedule, not a transcript quotation.

# 1. Delivery principles

Build the order control room first, because every other department record must connect back to an order.

Do not build a giant generic ERP. Build only the process actually used by the business.

Use a single database so the same RM/PM/order information is not entered twice.

Prototype early; validate with real users; remove unnecessary fields/stages before building deeper modules.

Keep workflow configurable so the client can simplify intermediate stages without code changes.

Migration and test data must run in parallel with module development, not at the very end.

# 2. 90-day roadmap

| Days | Phase | Main build | Exit gate |
| --- | --- | --- | --- |
| Days 1-10 | Discovery freeze + demo | Final field map, clickable/working demo of order register, wizard, basic Kanban, Order 360 | Client walkthrough and corrections |
| Days 11-20 | Core masters + order engine | Customer, Product, Variant, Packaging masters, Order Wizard, Order ID, document hub | Create real orders |
| Days 21-30 | Order control room | Excel table, Kanban, filters, repeat order, stage guard logic, activity timeline | Order flow UAT |
| Days 31-40 | R&D + Samples | R&D queue, formulation versioning, sample versions, feedback loop | R&D UAT |
| Days 41-50 | BOM + Artwork + Packaging | Multi-level BOM, conversion rules, artwork versions, QA/printing release, PM config | Production-readiness UAT |
| Days 51-60 | Procurement + GRN + Inventory | Shortage engine, PR, PO, approval, GRN, QC-incoming, stock ledger | Material lifecycle UAT |
| Days 61-70 | Production + Quality | Production planning, batch, machine/operator, output, waste, bulk QC, optional fill QC, final QC | Manufacturing UAT |
| Days 71-80 | Billing + Dispatch + Integration | Invoice, advance/balance, dispatch, payment gate, Tally sync scope | End-to-end UAT |
| Days 81-90 | Go-live preparation | Migration finalization, training, SOPs, role testing, bug fixes, production launch | Go-live + handover |

# 3. Detailed work breakdown

| # | Workstream | Scope | Output |
| --- | --- | --- | --- |
| 1 | Project setup | Environment, repo, CI/CD, base DB, master layout, audit framework | Platform ready |
| 2 | Masters | Customer, Product, Variant, RM, PM, Supplier, UOM, categories, test templates | Master-data import template ready |
| 3 | Order | Wizard, order lines, attachments, payment, verification, statuses | Order can be created end-to-end |
| 4 | Order Register | Excel-like table, filters, sort, saved views, row drill-down | Daily operations can move off Excel |
| 5 | Kanban | Configurable columns, stage guards, action dialogs | Stage changes are controlled |
| 6 | R&D/Samples | R&D case, formulation version, sample version, feedback | Sample loop is traceable |
| 7 | BOM | BOM tree, versions, RM %, UOM, on-hand, conversion, material demand | Demand calculates correctly |
| 8 | Artwork | Artwork versions, QA approval, printing release | Artwork history is complete |
| 9 | Procurement | Shortage -> PR -> PO -> approval -> vendor | PO lifecycle works |
| 10 | GRN/QC | Receipt, under-testing stock, QC, pass/fail | Approved stock only is usable |
| 11 | Production | Plan, batch, material issue, machine, operator, output, waste | Actual production is traceable |
| 12 | Filling/Packing | Bulk allocations, fill records, PM issue, pack completion | Finished goods count is accurate |
| 13 | Final Quality | Final QC/QA, rework loops | Dispatch gate works |
| 14 | Accounts/Dispatch | Billing, payments, Tally integration, dispatch | Order closes correctly |
| 15 | Migration | Historic customer/product/order/RM/PM data | Reconciled with source data |
| 16 | Training/UAT | Department walkthroughs, SOPs, fixes | Users sign off |
| 17 | Go-live | Cutover, opening balances, monitoring | ERP becomes day-to-day source |

# 4. Demo plan for the first 10 days

| Day | Demo content | User validation |
| --- | --- | --- |
| 1 | Shell + dashboard + left navigation | Navigation is understandable |
| 2 | Customer + Product + Variant masters | Master setup is correct |
| 3 | Order Wizard v1 | Can create a real order |
| 4 | Order Register | Feels like the existing Excel workflow |
| 5 | Kanban + stage guard dialogs | Moving a stage does not bypass work |
| 6 | Order 360 + document hub | All order information is in one place |
| 7 | R&D + Sample v1 | Sample tracking and feedback loop |
| 8 | BOM + shortage preview | RM/PM demand is visible |
| 9 | PO/GRN/QC concept | Material lifecycle is understandable |
| 10 | End-to-end mini scenario | Client lists fixes before deep build |

# 5. Data migration plan

| Wave | Data | Validation |
| --- | --- | --- |
| M1 | Customers + contacts + GST | Duplicate check |
| M2 | Products + variants + pack sizes | Product/variant mapping |
| M3 | RM master + PM master + suppliers | Codes/UOM/supplier validation |
| M4 | Formulations/BOM versions | Component/UOM/revision validation |
| M5 | Artwork references | Version and file-link validation |
| M6 | Order history + legacy statuses | Count/value reconciliation |
| M7 | Opening inventory | Physical/system reconciliation |
| M8 | Go-live delta | Final incremental import |

# 6. Testing strategy

| Test level | What to test | Exit condition |
| --- | --- | --- |
| Unit | Formulas, calculations, versioning | Developer tests pass |
| Integration | Order -> BOM -> shortage -> PO -> GRN -> QC -> stock -> production | Data flows correctly |
| Workflow | Stage guards, loops, failures, rework | No invalid bypass |
| Permission (later) | View/edit/approve/reject/override | Role matrix signed off |
| Migration | Counts, totals, relationships | Reconciliation signed |
| UAT | Real users use real scenarios | User acceptance |
| Go-live smoke | Create one order and trace to dispatch | End-to-end transaction succeeds |

# 7. Core UAT scenarios

| Scenario | Test steps | Expected result |
| --- | --- | --- |
| New order | Create customer -> order -> advance -> official | Order appears in register and Kanban |
| Sample loop | R&D -> Sample V1 -> feedback -> Sample V2 -> approval | History preserved |
| Repeat order | Clone approved previous order -> change qty | New order created; old order untouched |
| BOM shortage | Order demand exceeds approved stock | Shortage visible and procurement can be initiated |
| Incoming QC fail | GRN -> QC fail | Stock is quarantined; not usable |
| Bulk QC fail | Production -> QC fail | Batch returns to rework/hold |
| Production shortfall | Plan 100, produce 98 | Actual = 98; balance = 2 |
| Waste/return | Production has leftover | Disposition is captured |
| Bulk split | One bulk batch -> 10/20/30 ml allocations | No duplicate bulk manufacturing |
| Final QC fail | Packed FG -> final QC fail | Dispatch blocked |
| Payment gate | Invoice -> partial/full payment | Dispatch follows configured rule |
| Dispatch | Approved + payment satisfied | Dispatch and delivery complete order |

# 8. Go-live and support

| Period | Activity | Outcome |
| --- | --- | --- |
| Day 81-85 | Final migration + opening balances | Production data ready |
| Day 86-88 | Department training + SOP walkthrough | Users trained |
| Day 89 | Cutover rehearsal | Cutover issues identified |
| Day 90 | Go-live | ERP becomes day-to-day system |
| Days 91-120 | 30-day monitoring/training | Daily user support + process tuning |
| Days 121-150 | 60-day support window | Bug fixes, adoption support, small adjustments |

# 9. Change-control rules

Field changes should be classified as: required business rule, usability change, visual change, new module, or Phase 2.

Do not add a field merely because it existed in a generic ERP reference. Each field must map to a business action or report.

Do not add a new top-level stage unless it changes ownership or creates a required gate; otherwise use a sub-status/task.

Any change that affects historical data must preserve version/history.

Any change affecting stock or financial totals requires test cases before release.

# 10. Deliverables by go-live

| Deliverable | Target |
| --- | --- |
| Working ERP web application | Yes |
| Order Wizard + Register + Kanban + Order 360 | Yes |
| Customer/Product/Variant/RM/PM/Supplier masters | Yes |
| R&D + Samples + formulation versions | Yes |
| Multi-level BOM + demand calculation | Yes |
| Artwork + packaging + QA approval | Yes |
| PR/PO/GRN/QC + inventory states | Yes |
| Production + filling + packing + waste | Yes |
| Billing + payment + dispatch | Yes |
| Document hub + audit log | Yes |
| Migration templates + final migrated data | Yes |
| User SOPs + training | Yes |
| AI forecasting / AI repeat-order assistant | Phase 2 |

# 11. Next design freeze after this document

Approve the master end-to-end flow, especially order/advance/R&D sequencing.

Approve the exact Excel Order Register columns and their order.

Approve the legacy-status mapping.

Approve the multi-level BOM example and unit-conversion rules.

Approve the simplified PO and GRN formats.

Then freeze the role/permission matrix, hidden fields and exact Kanban positioning.

Begin the 10-day demo build against the signed field dictionary.